## Other
PMD-2021-FRM-108 _ V 1.2 | [6 empty] | INSPECTION NO: IR-1925
REQUEST FOR INSPECTION | [5 empty] | Housing Development Corporation Limited HDC Building, Hulhumalé, Republic of Maldives Hotline 1516 T +960 335 3535 E hello@hdc.mv W www.hdc.mv
Project Management Section
PROJECT MANAGEMENT & DEVELOPMENT
Project Details
Project |  | Installation Of Additional Elevators In Hiyaa Towers
Contractor |  | Shenyang Yuanda Intellectual Industry Group Co.Ltd
Contract No |  | HDC (161)-PMD/CNTR/2024/1
Client |  | Housing Development Corporation
Inspection Details
Ref. Drawing |  | HDC(161)-MNS/DEV/2024/12 |  | Date | 03/03/2026
Work Site |  | Hiyaa Towers |  | Time | 11:00
Location |  | H11
Received by [Client]
Name:
Designation:
Date:
Arrange Inspection for:
1 | COMPLETION OF CLADDING WORK
2 | GROUND FLOOR AND ROOF TO CEILLING
3
4
5
Weather condition:
Pre-Inspection checked by Contractor
Name: Prasad De Silva
Designation: Asst. Project Manager
Date: 02/03/2026
Comments (URBANCO USE ONLY):
Relevant Sub-clause/Term
Client Representative
Signature |  |  | Name:
Designation:
Date:
Contractor Representative
Name:
Designation:
Date: