## Cladding Frame
PMD-2021-FRM-108 _ V 1.2 | [11 empty] | INSPECTION NO: IR-1922
REQUEST FOR INSPECTION | [9 empty] | Housing Development Corporation Limited HDC Building, Hulhumalé, Republic of Maldives Hotline 1516 T +960 335 3535 E hello@hdc.mv W www.hdc.mv
Project Management Section
PROJECT MANAGEMENT & DEVELOPMENT
Project Details
Project |  | Installation Of Additional Elevators In Hiyaa Towers
Contractor |  | Shenyang Yuanda Intellectual Industry Group Co.Ltd
Contract No |  | HDC (161)-PMD/CNTR/2024/1
Client |  | Housing Development Corporation
Inspection Details
Ref. Drawing |  | HDC(161)-MNS/DEV/2024/12 |  |  |  | Date |  |  | 03/03/2026
Work Site |  | Hiyaa Towers |  |  |  | Time |  |  | 11:00
Location |  | H14
Received by [Client]
Name:
Designation:
Date:
Arrange Inspection for:
1 | INSPECTION FOR ENTRANCE CLADDING FRAME
2 | 1ST FLOOR TO 5TH FLOOR
3
4
5
Weather condition:
Pre-Inspection checked by Contractor
Name: Prasad De Silva
Designation: Asst. Project Manager
Date: 02/03/2026
Comments (URBANCO USE ONLY):
Relevant Sub-clause/Term
Client Representative
Signature |  |  |  | Name:
Designation:
Date:
Contractor Representative
Name:
Designation:
Date:
CHECKLIST FOR CLADDING FRAME INSTALLATION
PROJECT: |  |  | INSTALLATION OF ADDITIONAL ELEVATOR IN HIYA TOWERS
CLIENT: |  |  | HOUSING DEVELOPMENT CORPORATION
CONTRACTOR: |  |  | SHENYANG YUANDA INTELLECTUAL INDUSTTRY GROUP CO-LTD |  |  |  |  | Inspection #: |  |  | RFI-1922
CONTRACT NO |  |  | HDC (161)- PMD/CNTR/2024/1 |  |  |  |  | Date: |  |  | 2026-03-03
[8 empty] | Time: |  |  | 11:00
[8 empty] | Location: |  |  | H14
| WORKS INSPECTED |  |  |  | ü/û/NA |  | COMMENTS
All cladding frames installed as per approved drawings and specifications
Frames are vertically and horizontally aligned
No deformation or movement in the frame after installation
Box bars are free from rust, corrosion, and any surface damage
No sharp edges or protrusions that pose a safety risk
All weld joints cleaned properly after welding (e.g., removal of slag, spatter, oil, or dust)
Anti- corrosive coating applied evenly and covers the entire weld area
No flaking, peeling, or damage to the applied anti-corrosion coating
Comments on completed works:
Contractor Representative |  |  |  |  | Client Representative
Name: |  | Prasad De Silva |  |  | Name:
Designation: |  | Asst. Project Manager |  |  | Designation:
Signature: |  |  |  |  | Signature: