## Cladd. Inst. Cmpltn
PMD-2021-FRM-108 _ V 1.2 | [11 empty] | INSPECTION NO: IR-1925
REQUEST FOR INSPECTION | [9 empty] | Housing Development Corporation Limited HDC Building, Hulhumalé, Republic of Maldives Hotline 1516 T +960 335 3535 E hello@hdc.mv W www.hdc.mv
Project Management Section
PROJECT MANAGEMENT & DEVELOPMENT
Project Details
Project |  | Installation Of Additional Elevators In Hiyaa Towers
Contractor |  | Shenyang Yuanda Intellectual Industry Group Co.Ltd
Contract No |  | HDC (161)-PMD/CNTR/2024/1
Client |  | Housing Development Corporation
Inspection Details
Ref. Drawing |  | HDC(161)-MNS/DEV/2024/12 |  |  |  | Date |  |  | 03/03/2026
Work Site |  | Hiyaa Towers |  |  |  | Time |  |  | 11:00
Location |  | H11
Received by [Client]
Name:
Designation:
Date:
Arrange Inspection for:
1 | COMPLETION OF CLADDING WORK
2 | GROUND FLOOR AND ROOF TO CEILLING
3
4
5
Weather condition:
Pre-Inspection checked by Contractor
Name: Prasad De Silva
Designation: Asst. Project Manager
Date: 02/03/2026
Comments (URBANCO USE ONLY):
Relevant Sub-clause/Term
Client Representative
Signature |  |  |  | Name:
Designation:
Date:
Contractor Representative
Name:
Designation:
Date:
CHECKLIST FOR CLADDING INSTALLATION COMPLETION
PROJECT: |  |  | INSTALLATION OF ADDITIONAL ELEVATOR IN HIYA TOWERS
CLIENT: |  |  | HOUSING DEVELOPMENT CORPORATION
CONTRACTOR: |  |  | SHENYANG YUANDA INTELLECTUAL INDUSTTRY GROUP CO-LTD |  |  |  |  | Inspection #: |  |  | RFI-1925
CONTRACT NO |  |  | HDC (161)- PMD/CNTR/2024/1 |  |  |  |  | Date: |  |  | 2026-03-03
[8 empty] | Time: |  |  | 11:00
[8 empty] | Location: |  |  | H11
| WORKS INSPECTED |  |  |  | ü/û/NA |  | COMMENTS
Cladding panels installed as per approved shop drawings and specifications
Cladding type, color, pattern, and material match approved samples
Panels are level, plumb, and evenly spaced
Joints are uniform, consistent, and properly aligned
All protective films removed from panels & Panels cleaned and free from dust, adhesive marks, and scratches
Edge finishes and corner details are neat and professionally executed
Cladding is securely fixed to the frame &All fasteners (screws, rivets, anchors) are of correct type and properly installed
Joints and gaps sealed using approved sealant materials & No visible gaps that can cause water ingress
All edge trims, corner profiles, and expansion joints properly installed
Sealant application is clean and continuous
Comments on completed works:
Contractor Representative |  |  |  |  | Client Representative
Name: |  | Prasad De Silva |  |  | Name:
Designation: |  | Asst. Project Manager |  |  | Designation:
Signature: |  |  |  |  | Signature: